## Roadmap Overview
Phase | Timeline | Coverage | Key Objectives | Budget (KES) | Status
Phase 1: Pilot | Months 1-3 | 4 Counties (Kakamega, Samburu, Nairobi, Nyeri) | Test algorithm; train 500 officers; monitor fairness metrics; validate revenue | KES 45M | Active
• Deploy in county headquarters • Real-time fairness dashboard • Weekly monitoring reports
Phase 2: Regional | Months 4-9 | 15 Counties (expand from pilot areas) | Scale based on Phase 1 learnings; integrate with IPRS/NTSA/KRA; public awareness | KES 120M | Planning
• 1,500 officers trained • API integrations complete • Swahili communication campaign
Phase 3: National | Months 10-18 | 47 Counties (complete national coverage) | Full deployment; behavioral nudges; international partnerships | KES 280M | Planning
• 2,000+ officers trained • All 47 counties operational • Academic partnerships launched

## Key Metrics
Metric | Current | Phase 1 Target | Phase 2 Target | Phase 3 Target (National)
Enrollment Rate | 45% | 58% | 68% | 72%
Average Fairness Score | 32/100 | 55/100 | 68/100 | 76/100
Population Overcharged | 67% | 50% | 25% | 8%
Annual Revenue | KES 87B | KES 116B | KES 135B | KES 139B
Compliance Rate | 45% | 60% | 70% | 75%
Preventive Care Access | Base | +25% | +38% | +47%
Equalized Odds Gap | >5% | <5% | <3% | <2%
Audit Trail Coverage | 0% | 100% | 100% | 100%

## Budget
Category | Phase 1 | Phase 2 | Phase 3 | Total
Training & Capacity Building | KES 18M | KES 45M | KES 85M | KES 148M
Technology Integration | KES 15M | KES 30M | KES 60M | KES 105M
Monitoring & Evaluation | KES 8M | KES 25M | KES 65M | KES 98M
Communications & Awareness | KES 4M | KES 20M | KES 70M | KES 94M
TOTAL | KES 45M | KES 120M | KES 280M | KES 445M