# SHA PMT v2.1 Implementation Roadmap — Phase 0 to Full Deployment

## Executive Summary

The AGI model can be deployed in phases with full operational safety. This roadmap provides:

**Phase 0 (CAJ Compliance)**: Disclose algorithm, prove Data Protection Act compliance

**Phase 1 (Validation)**: Soft rollout to 20,000 test citizens across two pilot counties

**Phase 2 (Fairness Proof)**: Publish county-level fairness metrics; stakeholder engagement

**Phase 3 (National Deployment)**: Full rollout to all 22 million registered Kenyans

**Timeline: 4 weeks CAJ compliance → 8 weeks validation → 12 weeks full deployment**

---

## Phase 0: CAJ Compliance & Algorithmic Disclosure (Week 1–3)

### Objectives

[ ] File complete algorithm + HRIA with Data Commissioner

[ ] File CAJ response with SHAP sample explanations

[ ] Publish algorithm pseudocode on SHA website

[ ] Activate Data Protection Officer oversight

### Deliverables

**Week 1 (Now)**

[x] Algorithm pseudocode completed (see CAJ_21_DAY_DISCLOSURE.md)

[x] Human Rights Impact Assessment (30+ pages)

[x] AI Bill 2026 compliance checklist

[ ] SHAP explanation samples for 100 test cases (generated)

[ ] Data Commissioner briefing slide deck

**Week 2**

[ ] File with Data Commissioner + DPA Section 35 compliance proof

[ ] File with CAJ (algorithm + explanations + audit trail specification)

[ ] Media briefing: "SHA to Implement Algorithmic Transparency"

[ ] County coordinator briefing (prepare for Phase 1)

**Week 3**

[ ] Public announcement of AGI v2.1 on SHA website

[ ] USSD system readiness testing (*147# mock scenarios)

[ ] Data Commissioner certification letter

[ ] Data retention infrastructure (blockchain ledger) activated

### Success Criteria

✓ CAJ order satisfied on or before June 5 deadline

✓ Data Commissioner issues compliance certificate

✓ Zero media backlash on transparency (positive or neutral framing)

✓ USSD system passes load testing (100+ concurrent sessions)

---

## Phase 1: Validation & Soft Rollout (Week 4–8)

### Objectives

Prove AGI model produces fair outcomes across demographics

Validate USSD architecture stability

Generate fairness metrics for stakeholder engagement

Identify edge cases before national deployment

### Test Cohort Design

**Cohort A: Nairobi (10,000 citizens)**

Rationale: Urban, digitally literate, high M-Pesa penetration

Expected impact: High premium reduction for informal traders (KSh 1,500 → KSh 800)

Risk: Wealthy citizens may find loopholes (detects model vulnerabilities)

**Cohort B: Meru (10,000 citizens)**

Rationale: ASAL county, rural, mixed formal/informal

Expected impact: Significant subsidy expansion (exclusion error drops from 31% to 7%)

Risk: Low: Rural population baseline is high-error, hard to make worse

**Cohort C: Comparison Group (10,000 citizens)**

**Cohort D: M-Pesa Agents (500 citizens)
Rationale: Kenya has over 390,000 agents with high transaction velocity but low net commissions (KES 5,000-15,000/month).
Expected impact: Test the effectiveness of the 'retained balance vs. gross velocity' check. Verify that agent accounts are not overcharged due to float management.

Same demographics, USSD returns "old Lasso PMT result" (for A/B fairness comparison)

Used only for evaluation; actual billing still uses Lasso PMT until Phase 3

### Week-by-Week Execution

**Week 4: Recruitment & Data Prep**

[ ] Identify 20,000 test citizens (10k + 10k pilot, 10k control)

[ ] SMS invitation: "You've been selected to test new SHA fairness algorithm"

[ ] Send USSD *147*TEST# code to activate test sessions

[ ] Load 12-month M-Pesa histories from Safaricom (via data agreement)

[ ] Secure Safaricom MOU (Phase 0 dependency: commercial data agreement, spec alignment, DPA compliance, cost structure)

[ ] Load NTSA vehicle registry for test cohort

[ ] Load KRA tax pin status for cross-reference

**Week 5: Soft Rollout**

[ ] Go live: Nairobi & Meru citizens access *147*TEST#

[ ] Daily monitoring: 1,000–2,000 new classifications per day

[ ] Collect USSD session logs, response times, error rates

[ ] Monitor fraud flag triggers (document false positives)

[ ] Citizen feedback collection (SMS survey: "Did the explanation make sense?")

**Week 6: Fairness Analysis**

[ ] Generate county-level exclusion error rates

- Nairobi: Current 18% → Target <8%

- Meru: Current 31% → Target <9%

[ ] Generate demographic breakdowns (gender, age, urban/rural)

[ ] Compare SHAP explanations (are deductions clear to citizens?)

[ ] Measure compliance lift (how many current non-payers would re-enroll?)

**Week 7: Stakeholder Engagement**

[ ] Publish Phase 1 results to Data Commissioner

[ ] Present fairness metrics to civil society organizations

[ ] County government presentations (governors, health officials)

[ ] Media briefing: "Fairness Pilot Results Show Promise"

[ ] Lighthouse Reports engagement (offer anonymized fairness data by county)

**Week 8: Go/No-Go Decision**

[ ] Board decision: Proceed to national deployment or iterate?

[ ] **Success criteria for Go:**

- Exclusion error <10% in both counties ✓

- USSD uptime >99.9% ✓

- Citizen satisfaction >75% on explanation clarity ✓

- No major fraud exploits discovered ✓

- Data Commissioner satisfied with fairness metrics ✓

### Success Metrics (Phase 1)

| Metric | Target | Success |

|--------|--------|---------|

| Exclusion Error Rate (Nairobi) | <8% | Yes if achieved |

| Exclusion Error Rate (Meru) | <9% | Yes if achieved |

| Equalized Odds Gap (all demographics) | <0.05 | Yes if achieved |

| USSD Response Time (P99) | <2 sec | Yes if <1.8 sec |

| USSD Uptime | >99% | Yes if achieved |

| Citizen SHAP Comprehension | >75% understand deductions | Yes if survey shows clarity |

| Fraud Flags | <0.5% false positive rate | Yes if <1% flagged |

| Projected Compliance Lift | +50% payers | Yes if modeled |

---

## Phase 2: Fairness Proof & Stakeholder Alignment (Week 9–12)

### Objectives

Publish independent fairness audit

Achieve stakeholder buy-in (counties, civil society, international media)

Prepare operational infrastructure for national rollout

Address any residual concerns

### Week 9: Fairness Audit Publication

**Public Report: "SHA PMT v2.1 Fairness Analysis — Pilot Results"**

County-level exclusion error comparison (current vs. proposed)

Demographic breakdowns: gender, age, urban/rural parity analysis

SHAP transparency metrics: average explanation clarity scores

Fraud prevention effectiveness: false positive analysis

Data Protection Act compliance certification

**Published to:** SHA website, Data Commissioner, media, international outlets

**International Outreach**

[ ] Engage Lighthouse Reports and Africa Uncensored on AGI solution framework (re-contact post-publication of their May 4 investigation)

[ ] Offer Commonwealth Union: "Case Study of Algorithm Reform in Kenya"

[ ] Brief international development partners (IMF, World Bank health programs)

[ ] Position as reference implementation for African healthcare AI

### Week 10: Stakeholder Alignment

**County Governors (All 47 Counties)**

[ ] Present Phase 1 fairness data (how their county benefits)

[ ] Address concerns (will my county be fairly assessed?)

[ ] Secure political buy-in for Phase 3 (county liaison officers needed)

**Civil Society Organizations**

[ ] Engage health equity NGOs (AMREF, Doctors Without Borders Kenya)

[ ] Engage consumer protection groups

[ ] Engage disability rights organizations (present CHE exemption)

[ ] Seek letter of support: "AGI model advances health equity"

**Labor Unions**

[ ] Engage COTU (Central Organisation of Trade Unions)

[ ] Engage informal sector associations (jua kali, bodaboda networks)

[ ] Demonstrate premium reduction for workers

[ ] Secure union statement: "Supports fairness-driven algorithm"

**Parliamentary Health Committee**

[ ] Present fairness audit to committee

[ ] Answer questions on legal compliance (AI Bill, DPA, CAJ)

[ ] Secure motion of support (if possible)

[ ] Prepare for hostile questioning (opposition may raise concerns)

### Week 11: Operational Infrastructure

**National USSD Rollout Preparation**

[ ] Coordinate with Safaricom, Airtel, Telkom (all three MNOs)

[ ] Validate load testing: 500 TPS (transactions per second) sustained

[ ] Failover testing: if Safaricom gateway fails, Airtel takes traffic

[ ] Emergency protocol: if system crashes, default to Lasso PMT (not random)

**County Infrastructure**

[ ] Appoint county-level appeal officers (one per county, trained on SHAP)

[ ] Set up county-level human review offices (for escalations)

[ ] Train 200 staff on AGI algorithm, SHAP explanations, fairness concepts

[ ] Activate fraud investigation unit (30 investigators)

**Media & Public Communications**

[ ] Prepare public-facing website explainer: "How the New Algorithm Works"

[ ] Create USSD tutorial videos (Swahili, English, Kikuyu, Luo)

[ ] Activate FAQ hotline (*147*4# for AI Bill compliance)

[ ] Pre-empt misinformation with factual messaging

### Week 12: Final Review & Go Decision

**Board Decision: Proceed to National Deployment?**

**Go/No-Go Criteria:**

[ ] Phase 1 fairness metrics certified by Data Commissioner? ✓

[ ] County governors publicly supportive? ✓

[ ] Civil society letter of support obtained? ✓

[ ] USSD infrastructure load tested to 500+ TPS? ✓

[ ] 200 county staff trained and certified? ✓

[ ] Zero critical bugs in fraud detection? ✓

[ ] Media sentiment neutral or positive? ✓

**If Go:**

→ Proceed to Phase 3 (national deployment, week 13+)

**If No-Go:**

→ 2-week iteration sprint, then re-evaluate

### Success Metrics (Phase 2)

| Metric | Target |

|--------|--------|

| Fairness audit published | Yes, public website |

| County governor support | >40 of 47 public supporters |

| Civil society letter | Yes, from 3+ major organizations |

| Media sentiment | Neutral or positive |

| Parliamentary mention | At least one committee briefing |

| Staff training completion | 100% of 200 county staff |

| USSD load test | 500+ TPS, <2 sec response |

| International media pickup | At least 1 major outlet (Lighthouse, Commonwealth) |

---

## Phase 3: National Deployment (Week 13–24)

### Objectives

Deploy AGI model to all 22 million registered Kenyans

Maintain financial stability during transition

Collect full fairness data across all 47 counties

Establish permanent operations

### Deployment Strategy

**Week 13–15: Soft Launch (1M citizens)**

[ ] Roll out to 1 million test citizens (randomly selected across all 47 counties)

[ ] Monitor exclusion error rates by county in real-time

[ ] Daily calls with county teams to surface issues

[ ] Document any edge cases (unusual households, fraud patterns)

**Week 16–18: Phased National Rollout**

[ ] Week 16: 5M citizens (27% of target)

[ ] Week 17: 10M citizens (45% of target)

[ ] Week 18: 22M citizens (100% of target)

Each phase: Monitor fraud flags, fairness metrics, USSD uptime, premium changes

**Week 19–24: Stabilization & Audit**

[ ] Annual fairness audit: exclusion/inclusion error rates all 47 counties

[ ] Annual report to Data Commissioner (compliance certification)

[ ] Monthly fraud investigation summaries (arrests, case dispositions)

[ ] Public dashboard: county-level fairness metrics, system uptime, appeals processed

### Financial Transition Safety

**Premium Revenue Modeling**

| Cohort | Current Avg Premium | AGI v2.1 Premium | Pop. | Current Annual | AGI Annual | Change |

|--------|-------------------|------------------|------|-----------------|----------|--------|

| Band 1 (Indigent) | KSh 300 | KSh 300 | 7.5M | KSh 27B | KSh 27B | — |

| Band 2 (Low) | KSh 1,200 | KSh 300 | 8M | KSh 115B | KSh 29B | -75% |

| Band 3 (Mid) | KSh 1,500 | KSh 870 | 5M | KSh 90B | KSh 52B | -42% |

| Band 4 (High) | KSh 1,500 | KSh 2,500 | 1.5M | KSh 27B | KSh 45B | +67% |

| **Total Informal** | — | — | **21.5M** | **KSh 259B** | **KSh 153B** | **-41%** |

**But compliance increase offsets this:**

| Scenario | Current Compliance | AGI Compliance | Revenue Lift |

|----------|-------------------|-----------------|--------------|

| Current Model | 22.7% (5M payers) | — | — |

| AGI Model (lower premiums) | 60% (13.6M payers) | — | — |

| Projected Annual Revenue | KSh 87B | KSh 139B | **+53%** |

**Revenue Safety: Deployment Pauses if**

[ ] Monthly revenue drops >20% below KSh 11B (would indicate catastrophic opt-out)

[ ] This triggers automatic 48-hour pause, audit, and adjustment

### Success Metrics (Phase 3)

| Metric | Target | Month 6 |

|--------|--------|---------|

| Active payers nationwide | 13.6M (60%) | Measure |

| Avg premium (informal) | KSh 850 | Measure |

| Exclusion error rate (national) | <10% | Measure |

| Exclusion error (all 47 counties) | <12% each | Measure |

| Equalized Odds gap | <0.05 | Measure |

| Annual revenue | KSh 139B+ | Measure |

| Payout ratio | <70% | Measure |

| Fund sustainability | No Treasury bailout | Target |

| Fraud losses | <KSh 1B annually | Measure |

| Citizen satisfaction | >70% satisfaction with SHAP | Survey |

| Data Commissioner compliance | 100% audit approval | Certification |

---

## Political Risk Mitigation

### Risk 1: Ministry Reputation Loss ("Admitting Failure")

**Risk:** Government reluctant to acknowledge Lasso PMT was broken

**Mitigation:** Frame as "Optimization" not "Replacement"

Message: *"SHA PMT v2.1 is the refinement we promised. It keeps the 2.75% rate, improves fairness, and increases revenue."*

Reference: SHA's own public statement (May 2026) committing to "refine the means testing tool"

Political cover: Position as fulfilling Bottom-Up Economics mandate

### Risk 2: Union Pushback (Formal Sector Worried About Higher Premiums)

**Risk:** Formal sector workers see AGI increases and blame government

**Mitigation:** Communicate the math clearly

AGI increases only for high-income formal sector (>KSh 450k annually)

Majority of formal sector (salaried workers) unaffected (still 2.75% of salary)

Emphasize: High-income workers paying fair share enables subsidy for poor

**Union Engagement:**

Early briefings with COTU leadership

Show that fund sustainability = job security (healthcare workers)

Highlight: Informal sector re-entry means more premiums to support fund

### Risk 3: Media Narrative ("Government Still Stealing from Poor")

**Risk:** Opposition media frames AGI as insufficient change, continues "SHA is broken" narrative

**Mitigation:** Lead with transparency

Publish full algorithm pseudocode (not just summary)

Publish fairness audit results by county

Invite Lighthouse Reports and Commonwealth Union to validate

Position as global reference implementation (positive frame)

### Risk 4: Technical Failure During Rollout

**Risk:** USSD system crashes, fraud detection breaks, creates chaos

**Mitigation:** Phased approach with safety valves

Phase 1: Test with 20,000 before any permanent changes

Phase 2: Fairness validation with Data Commissioner oversight

Phase 3: Phased national rollout (1M → 5M → 22M)

Emergency protocol: If system fails, default to Lasso PMT (not random)

Weekly calls with Safaricom/Airtel technical teams

### Risk 5: Wealthy Citizens Finding Loopholes

**Risk:** High-income citizens exploit AGI deductions to appear poorer

**Mitigation:** Fraud detection + triangulation

Fraud flags trigger automatic escalation (KRA cross-check, NTSA verification)

Citizens flagged cannot re-appeal for 6 months (cooling-off period)

Data Protection Officer oversees fraud investigation fairness

Publish monthly fraud statistics (shows system catching exploits)

---

## Success Definition

**Phase 0 Success:** CAJ order satisfied, Data Commissioner certifies compliance, algorithm publicly disclosed

**Phase 1 Success:** Fairness pilot proves exclusion error <10%, USSD stable, citizen satisfaction >75%

**Phase 2 Success:** Fairness audit published, counties aligned, civil society support secured, operational readiness achieved

**Phase 3 Success:** National deployment complete, fund solvent (payout ratio <70%), compliance >60%, zero Treasury bailout required

---

## Conclusion

The AGI model can be deployed with confidence through this phased approach. Each phase provides opportunity to validate, adjust, and build stakeholder buy-in before full national rollout. By Week 24, SHA PMT v2.1 should be the operational standard with demonstrable fairness improvements and financial sustainability.

The key to success: **Transparency + stakeholder engagement + technical safety + phase gates.**

## Political Adoption Pathway

To ensure institutional adoption, the following 4-step path is established:
1. Academic & Policy Validation: Formulate KCA policy brief with Dr. Rotich and seek KIPPRA endorsement.
2. Legislative Entry Point: Present the AGI model to the National Assembly Departmental Committee on Health.
3. Zero-Commitment parallel run: Implement a side-by-side run (Phase 0 pilot) without replacing the current vendor system upfront.
4. Phased National Integration: Deploy as a schema update only after parallel-run data proves effectiveness.